## University of Iowa Fraternity & Sorority Life (FSL)Alcohol Harm Reduction Work Group Update, March 2018

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal | Key Tactics | Responsible Parties | Proposed Timeline | Updates |
| *Revise judicial processes* | * Provide training to councils and chapters
* Revise Code of Student Life
 | * Office of the Dean of Students
* Center for Student Involvement & Leadership
* Interfraternity Council
* Panhellenic Council
* National Pan-Hellenic Council
* Multicultural Greek Council
 | January-March 2018 | * Kim Novak (consultant in campus safety, student risk management, and student organization development) will visit campus in August 2018
* Revision of Code of Student Life will commence when new Dean of Students arrives
* To be created chapter scorecards will include judicial status and summary of cases
* Judicial training will be completed spring 2018
 |
| *Implement new guidelines for events with alcohol* | * Host luncheon meetings with area event venues to increase communication and collaboration
* Link ability to hold events with alcohol to chapter completion of key trainings
 | * Center for Student Involvement & Leadership
* FSL Advisory Committee
 | January-May 2018 | * Two meetings completed with event venues and downtown establishments, which included approximately 50 attendees from area businesses
* Feedback from venues about pilot events has been positive and venues are checking with FSL staff about event details if there are questions
* Work Group reviewed compliance sheets from pilot events and identified additional areas to focus on in terms of training:
	+ Event monitors should be introducing themselves to venue staff and security officers
	+ Guest list with ages and IDs should be cross-referenced
	+ We will request UI Public Safety officers add more comments and record when they went to each event and how long they were present
* Work Group will review cumulative assessment data about pilot events and recommend any changes to policy in May
* UI was chosen as a pilot campus for new National Interfraternity Council initiative to change the culture within fraternal organizations, and pilot event guidelines will be used within the project. Pilot launch date: April 8th
 |
| *Implement new guidelines for events without alcohol* | * Revise guidelines
* Improve communication of campus event opportunities
* Enhance collaboration between FSL and campus programming entities
 | * Center for Student Involvement & Leadership
* Governing councils
 | January-February 2018 | * Governing councils reviewed the materials the Work Group provided to guide this effort
* Panhellenic Council passed new bylaws governing events without alcohol, including:
	+ Chapter members must attend one event without alcohol for each event with alcohol they choose to attend
	+ Chapters may register events without alcohol that occur at various times, but must hold at least two events without alcohol on Thursday/Friday/Saturday evening after 8 p.m.
	+ Chapters must host at least one event without alcohol with a student organization other than a Greek organization
* New guidelines for events without alcohol are on the agenda for Interfraternity Council discussion this semester
 |
| *Re-deploy staff efforts* | * Increase staffing in FSL
* Redesign work to ensure time is focused on highest priority tasks
* Establish a standing FSL Advisory Committee
 | * Center for Student Involvement & Leadership
 | January-May 2018 | * FSL staff members are participating in the Work Group
* Work Group will recommend advisory structure at end of spring semester
* Additional staff members added in FSL have provided expanded capacity
 |
| *Provide effective evidence-based harm reduction programming* | * Implement Alcohol Skills Training Program (ASTP)
* Implement event monitor training
 | * Student Health & Wellness
* Center for Student Involvement & Leadership
 | Spring 2018 | * Event monitor training to launch in March. Event monitors are required at all events with alcohol. Their role is to identify and address problematic behavior, in collaboration with event staff and chapter leaders. At least one event monitor is required per 20 guests
* ASTP launched; 228 individuals have completed including students enrolled in the FSL leadership course
 |
| *Increase transparency in the FSL community* | * Constitute FSL Advisory Committee
* Revise the FSL website
* Create chapter scorecards
* Revise roster submission processes
* Determine a sustainable process for sharing judicial outcomes and quarterly progress updates
 | * Student Life Marketing + Design
* Center for Student Involvement & Leadership
* Office of the Dean of Students
 | Spring 2018 | * Work Group members reviewed score cards from aspirant campuses
* Draft scorecard will be discussed at an upcoming meeting
* Scorecard will be finalized and rolled out no later than August 2018
 |